## Slide 1
CDC Health Equity Grant
Strategy 2 – Activity 3
Healthy Suburban Cook Survey & Health Atlas

## Slide 2
Outline
 | Coordination | 3-4
 | Objectives of working with RTI | 5-6
 | Timeline for Objective 1 | 7
 | ​Roles and responsibilities for Healthy Suburban Cook Survey | 8
 | Objectives of working with Metopio & UIC | 9
 | ​Roles and responsibilities for Health Atlas | 10-11
 | ​Dashboard Examples | 12-18
2

## Slide 3
Actions needed to support the transparency include
Clear Roles and Responsibilities
Define the accountable and responsible parties for data access, training, customize reports. Plan to share with and get feedback on them from Quatrics.
Agreed-Upon Expectations for work product
Identify several projects that will build our understanding of challenges, barriers, and opportunities that can influence health of our communities and populations.
Visibility to Epidemiologic Analysis
Use public health data, social determinates of health, and geographies to evaluate health equity.
Data-Driven Rationale
Plan analysis, execute plan, review product. Tie timeline and analyses to progress against plan.
Where will data analysis products be stored? And how to share the products?
Coordination
The partnership between CCDPH and RTI & Metopio is critical to understanding the vaccination efforts of CCDPH, health disparities within SCC, and how the COVID vaccine needs can be addressed in the community. Working together to execute a two-year plan on developing useful reports, maps, and dashboards to be used for the purpose of decision making.
This drafted plan aims to address the resources and needs of the Healthy Suburban Cook County Survey and the Healthy Cook Atlas which will be developed in concert with the HSCCS

## Slide 4: Project Organizational Chart
CCDPH
RTI
CDPH
Nicole Lee Project Manager
Meha Singh
Project Manager
TAYLOR LEWIS Title/Role
ANDY PEYTCHEV Title/Role
DAIN PALMER
Title/Role
NAOMI FREEDNER
Title/Role
Kyla Quigley
CSTE Fellow/Coordinator for CCDPH
RISHI KOWALSKI Epidemiologist
NHAN NGUYEN Epidemiologist
C. SCOTT SMITH Epidemiologist
ALFREDA HOLLOWAY-BETH
Director of Epi
NIK PRACHAND Director of Epi
KINGSLEY WEAVER Epidemiologist

## Slide 5
Healthy Suburban Cook Survey
Objectives of Working with RTI
Behavioral Risk, Environmental Exposure, and Health Outcomes in Suburban Cook County
To conduct the 2022 Suburban Cook County survey of behavioral risk, environmental exposures, and health outcomes.
  Survey Development
  Sampling
  Data Collection
  Analysis/Reporting
  Data Visualization

## Slide 6
Suburban Cook Health Atlas
Objectives of Working with RTI
What should be in the Health Atlas
To review Chicago Health Atlas
  To determine what we should be on our health atlas
  Update cadence
  Dashboard Development

## Slide 7: Timeline for Healthy Suburban Cook Surveys
January - March 2022
- Get Access for all users
- Training
- Review platform
May-June 2022
- Conduct Analysis
- Create custom reports, maps, dashboard
December 2022
- Finalize reports, maps, and dashboards with branding and dissemination plan
March - May 2022
- Identify
June - November 2022
- Submit reports, maps, and dashboard drafts for review and approval

## Slide 8
Healthy Suburban Cook Survey
Municipality Grouping
Methodology
Threshold for grouping municipalities: 8,000 adult population
Factors determining grouping: CCDPH District, Similar SVI, population size, proximity
[how munis with small populations were grouped]

## Slide 9
Roles and Responsibilities 1/2
# | Item | Comment | Responsible | Role
1 | Survey length | By January 15, 2022 | Alfreda Holloway-Beth – CCDPH | Provide the number of questions and pages for the HSCS including any module surveys
2 | Sample size | Coordinate with Epi team to determine what geographies for SCC that will render a sample size for the total population and sub-jurisdictional areas | Taylor Lewis – RTI Nhan Nguyen – CCDPH C. Scott Smith – CCDPH | CCDPH will provide RTI with jurisdictional files to help with determining sample size. RTI will provide sample size by geographic granularity to help with estimated costs.
3 | Sampling methodology |  | Taylor Lewis – RTI | 
4 | Participant incentive structure |  |  | 
5 | Language Translation |  |  | 
6 | Drop points |  |  | 
7 | Data processing |  |  | 
8 | Detailed project schedule |  |  | 
9 | Management plan |  |  | 
10 | Project organization charts |  |  | 
7
Roles and Responsibilities – Healthy Cook County Survey

## Slide 10
Suburban Cook Health Atlas
Objectives of Working with UIC & Metopio
What should be in the Health Atlas
To review Chicago Health Atlas
  To determine what we should be on our health atlas
    Add indicators?
      Ex:
        Law enforcement involved injuries and mortality
        Greenspace
  Update cadence
  Dashboard Development

## Slide 11: Timeline for Suburban Cook Health Atlas
January - March 2022
- Get Access for all users
- Training
- Review platform
May-June 2022
- Conduct Analysis
- Create custom reports, maps, dashboard
December 2022
- Finalize reports, maps, and dashboards with branding and dissemination plan
March - May 2022
- Identify
June - November 2022
- Submit reports, maps, and dashboard drafts for review and approval

## Slide 12
Roles and Responsibilities 1/2
# | Item | Comment | Responsible | Role
1 | Platform Access |  |  | 
2 | Training |  |  | 
3 | Check-ins |  |  | 
4 | Identifications of data analysis projects using Qualtrics platform |  |  | 
5 | Dissemination Planning |  |  | 
6 | Communications Planning |  |  | 
Roles and Responsibilities – Suburban Cook Health Atlas

## Slide 13: Examples of the Dashboard

## Slide 20: Comparing Chicago Justice Qs vs BJS Qs
Add this post call;

## Slide 21: Overall – How to Add/Subtract Qs